## Summary
ID | Status | Date identified | Relevant deliverable or subsystem | Identified in Git commit ID… | Title | Requesting organization | Name of Requesting Person | Description | Customer ranking | Team ranking | Composite ranking | Status log (please date entries) | Date committed | Commited by (name) | Assigned to (name) | Resolution deadline | Date resolved | Resolved in Git commit ID… | Resolved by (name) | Date accepted | Accepted by (name)
0 (example) | Committed | 2020-01-01 | Frontend |  | Short description of issue | Options: Working Group, MORPC, CURA | Porr | Detailed description of issue | 1 | 2 | 1.5 | 1/1/2020 - Describe any progress or decisions made with respect to the issue. Please include the date and your name/initials | 2020-04-30 | Porr |  |  |  |  | Liu
2 | Pending | 2020-01-06 | Frontend | e2e5320f | Convey units of measure | CURA | Porr | Reader needs to know what are the units of the variable being displayed on the card. Consider doing this in narrative text, by adding y-axis labels, in the legend, or by another means. |  | 10 |  | 3/5/2020 - Y-axis now shows unit of measure. Currently hard-coded. Should be retrieved via API. |  |  | Jialin
8 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Identify counties on map | Working Group | Multiple |  |  | 10 |  | 3/5/2020 - Adam is considering using labelgun or Leaflet.labels instead. Fallback to custom basemap. 2/20/2020 - County name is reported on mouseover. Additionally, Adam intends to create a grey basemap with labels. |  |  | Adam
9 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Allow user to see details of data shown on map | Working Group | Multiple |  |  | 10 |  | 2/20/2020 - Indicator value for currently-selected time period is reported on mouseover. Unit of measure not currently included. |  |  | Jialin
10 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Cards are malformated after resizing browser window | Working Group | Kim |  |  | 10 |  | 2/20/2020 - Works well when cards are in expanded mode. Cards are still malformated in compact mode. |  |  | Jialin
11 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Card ordering is not preserved after click-and-drag rearrangment | Working Group | Kim |  |  | 10 |  |  |  |  | Jialin
23 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Add legend to map | Working Group | Stein |  |  | 10 |  | 3/5/2020 - Mouseover issue is fixed. Show unit of measure? 2/20/2020 - Getting close! Mouseover highlighting function breaks when filter range is set. |  |  | Jialin
25 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Add explanation of question mark symbol in landing page | CURA | Porr |  |  | 10 |  |  |  |  | Adam
26 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Colors on stacked bar charts are difficult to see/distinguish | Working Group | Stein |  |  | 20 |  | Consider using chroma.js |  |  | Jialin
28 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Provide indication of no data on map | Working Group | Unknown | If no map data is available for the chart feature the user has selected, indicate this explicitly |  | 20 |  | 3/5/2020 - No Data is reported in info box below map, but disappears when mouse moves off data point in card. |  |  | Jialin
30 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Better indication of linkage between card and map | Working Group | Multiple | User should be able to determine what data is being shown on the map rapidly and with little effort. User should be able to move gaze from map to cards and quickly locate the corresponding data. |  | 20 |  | 3/5/2020 - "Locked" data appears in red on the card. Luyu is addressing a few remaining bugs. |  |  | Luyu
31 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Documentation of indicator construction | Working Group | Multiple | Some users would like to better understand how indicators are computed and from what input data. Would prefer to display this in the dashboard rather than navigating away from the page if possible. |  | 20 |  | 3/5/2020 - Need to consider how to implement this and gather feedback from MORPC (and ideally WG) 2/20/2020 - Consider including this in "supplementary information" |  |  | Adam
15 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Allow downloading of derived indicator data | Working Group | Multiple | Provide simple and intuitive means for users to download spatiotemporal indicator data in forms usable by common tools. For each indicator, available data should include at least the following: 1. Tabular data for region by time period (readable by Excel) 2. Tabular data for all counties by time period (readable by Excel) 3. Spatial data (geometry + attribute table) for all counties by time period (readable by ArcGIS) |  | 20 |  | 3/5/2020 - Item 1 is working. Use unit of measure for column header. Luyu is working on items 2 and 3. Spatial data will be provided as KML. |  |  | Luyu
35 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Detailed supporting information | Working Group | Multiple | Some users would like to see additional contextual information related to the indicators, potentially including text, maps, imagery, hyperlinks. Would prefer to display this in the dashboard rather than navigating away from the page if possible. |  | 20 |  | 3/5/2020 - Need to consider how to implement this and gather feedback from MORPC (and ideally WG) |  |  | Adam
42 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Make data available via standard API(s) | Working Group | Elhami | Make spatiotemporal indictor data available for retrieval by ArcGIS directly from the network (download not required). At minimum, ArcGIS Online should be supported. Ideally ArcGIS Pro and ArcMap as well. |  | 20 |  | 3/5/2020 - Luyu is considering how to do this. Data will likely be exposed as KML. |  |  | Luyu
33 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Improve card rearrangement | Working Group | Multiple | Card arrangement by dragging has been described as clunky, difficult, non-intuitive by working group members. Need to improve usability of this feature, or eliminate it. |  | 40 |  |  |  |  | Jialin
38 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | More descriptive titles for basemaps | Working Group | Unknown |  |  | 40
40 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Indicator summary export | Working Group | Unknown | Graph + map + supporting info |  | 60
1 | Pending | 2020-01-06 | Frontend | e2e5320f | Style of narrative text box is confusing | CURA | Miller | The narrative text boxes on the cards seem like they should be editable, based on the box and border formatting. Perhaps that should be changed. |  | 99
3 | Pending | 2020-01-06 | Frontend | e2e5320f | Refine legend label word selection | CURA | Miller | Some legend labels are too wordy or do not accurately describe the data. Refine word selection. |  | 99
4 | Pending | 2020-01-06 | Frontend | e2e5320f | Handle overflow of legend label text | CURA | Miller | Some legend labels are too wide for the allocated space and appear truncated. Consider ways to display the full text. |  | 99
5 | Pending | 2020-01-06 | Frontend | e2e5320f | Baseline and target line are not prominent enough | CURA | Miller | Baseline and target line do not stand out enough. Consider changing their style to make them more prominent. |  | 99
6 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Allow adjustment of chart axis scales | Working Group | Kim |  |  | 99
7 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Allow precise interpretation of map data | CURA | Porr | January usability testing showed that users could not reliably discern relative values of the data shown on the map. Add features to improve interpretation of map features. |  | 99
12 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Tool does not adequately address use case #5 (TBD) | Working Group | Kim |  |  | 99
13 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Narrative text is difficult to read | Working Group | Kim | "Narrative text is quite small. Might be good to have a pop-out option to see it larger" |  | 99
14 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Allow layering of indicators | Working Group | Kim |  |  | 99
16 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Allow the user to change the indicator displayed on the map directly | Working Group | Kim |  |  | 99
17 | Pending | 2020-01-28 | Frontend | 96d1c9c3 | Numbers on charts are difficult to read | Working Group | Milam |  |  | 99
18 | Pending | 2020-02-04 | Frontend | N/A | Support hyperlinks in narrative text | MORPC | Schill | Narrative text boxes on Dashboard should allow for the inclusion of hyperlinks to direct users to external supporting information. |  | 99
19 | Pending | 2020-01-30 | Frontend | 96d1c9c3 | Allow resizing of map | CURA | Phillips | Allow resizing of sidebar to make the map more prominent. |  | 99
20 | Pending | 2020-01-30 | Frontend | 96d1c9c3 | Persistant scrollbars | CURA | Phillips | Add option to make scrollbars visible at all times. |  | 99
21 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Air quality heatmap | MORPC | Hurst |  |  | 99
22 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Audio narration for tutorial | Working Group | Shockey |  |  | 99
24 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Add pop-ups to map features | Working Group | Multiple |  |  | 99
27 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Card autoarrange | Working Group | Unknown |  |  | 99
29 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Support for Internet Explorer | Working Group | Sowry |  |  | 99
32 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Full-featured map | Working Group | Multiple | Add data, overlay, swipe, storymap |  | 99
34 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Support for small-format devices | Working Group | Multiple |  |  | 99
36 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Dashboard is too dense | Working Group | Multiple |  |  | 99
37 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Choropleth symbology for map | Working Group | Unknown |  |  | 99
39 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Undo of card rearrangement | Working Group | Unknown |  |  | 99
41 | Pending | 2020-02-11 | Frontend | 96d1c9c3 | Add pop-ups to chart features | Working Group | Multiple |  |  | 99
42